# RIMPAC 2000: Exercise “Strong Angel”

Eric Rasmussen, MD, FACP

## Third Fleet Surgeon

619-524-9541 shipboard

619-925-7701 cellular

rasmused@coronado.navy.mil

24 May 2000

Underway for RIMPAC

Final Outline

Recognizing that this is a first effort and everything will be hard, our goal in this exercise will be an effective legacy for those who will do this next time.

- Overview:

  - During a period of escalating tensions between two island nations, the United Nations requests a Coalition Task Force to serve as a calming presence in the waters off the most affected of the islands. On that island are two countries, Green (the good guys) and Orange (not the good guys). Ethnically Green citizens of Orange are subjected to persecution and flee across the border into Green. The influx worries Green, which requests assistance in the management of the refugees. The UN Secretariat agrees, and a civil-military operation is initiated that has UN agencies working with the Coalition militaries to establish a refugee camp in Green. Those agencies (UN High Commissioner for Refugees (UNHCR), World Food Programme (WFP), United Nations Children’s Fund (UNICEF), coordinated by the United Nations Office for the Coordination of Humanitarian Assistance (UN-OCHA), are to be supported in any fashion they deem desirable by elements of the Coalition military.

  - The camp will be established on the northwest corner of the Big Island of Hawaii. The site, called Puu Paa, is below an 800-foot hill, facing down slope across very rough lava scrublands to the ocean visible about 12 miles away. There will be two sites, the refugee camp itself and a Civil-Military Operations Center (CMOC) area about 3 miles east near Hwy 190. There will be a number of appropriate family tents within the camp, with a few larger tents for various support functions including meals, showers, recreation, admin, and bulk commodity storage. The CMOC section will contain more tents for storage, communication links, staff housing, experimentation, and various public relations areas for visitors.

  - We will support roughly 125 live volunteers for about five days in the camp. The volunteers will be primarily Red Cross Disaster Services volunteers playing refugees, sourced locally on the Big Island, and will be selected for their suitability to the rigors of several days in a potentially harsh environment. We note that there is nothing in the area. No power, water, food, or shelter. All facilities must be developed from scratch. Fortunately, the camp will be less than six miles from a small city with excellent medical facilities, and the site surveys have been reassuring. Obviously, the safety of the civilian volunteers will be paramount.

  - The material for the camp will be loaded onto an amphibious ship (probably the USS Boxer) and transported from Oahu to the landing area at K-docks on the Big Island. Working with CSSG-3 of 3rd Marines we anticipate transport by truck convoy from those docks and to establish the camp to UN specifications on the 9th and 10th of June. Refugees will probably begin arriving on the 10th, with most arriving on the 11th. The breakdown of the camp will be done on the 15th and 16th of June, with most material remaining on the Big Island for future exercises.

  - There will be an extensive experimental component to Strong Angel. One section in the CMOC area will be dedicated to the trials of information management in an austere environment. The experiments run the gamut from high-bandwidth informatics support, to the interviewing of refugees for event documentation in foreign languages, to alternative energy power generation.

  - There is a special effort to understand chemical and biological response capabilities for information management. A sub-exercise, called Sea Breeze (for CBRE, Chemical-Biological-Radiological-Envirotoxic) will stimulate the requirements that will test the primary experimental effort, a DARPA project called TIDES. TIDES is an acronym for Trans-lingual Information Detection, Extraction, and Summarization. It is a web portal with five major parts that link to resources not previously available. It will have its initial test in our attempt to ferret out the circumstances surrounding a Sudan-like event.

    - Real-World background: On 23 July 99, rumors surfaced that a chemical agent may have been used in Sudan against a civilian population. Evaluating that report proved challenging, so the TIDES Portal under development has been adapted to look at a similar question in this exercise.

    - In addition, we will have a malignant contamination of a water source within the camp by Orange insurgents masquerading as refugees. Our response to that will be designed to assess information management tools with particular attention to epidemiology in refugee camps, and the appropriate response.

    - NOTE: We will NOT be managing a chem-bio casualty problem. These experiments are to test information management tools. There will be no release, no casualties, no moulage, no MOPP gear, no decontamination procedures, and no general alerts to the refugees. Sea Breeze is more than a CPX, less than the full drill, and designed to exercise new information tools for an austere environment. Nothing more.

- Any questions regarding any facet of the exercise can be directed to the Officer Conducting the Exercise (OCE), LCDR Eric Rasmussen, Medical Corps, USN, the Fleet Surgeon for Third Fleet. Contact details are at the head of this paper.

- Dates (somewhat flexible)

  - 06 June: Coronado sails to BI from PH, Boxer arrives in PH same day

  - 07 June: Coronado off BI, Boxer onloading Oahu, and Site Team ashore

  - 08 June: Coronado pierside in Kona, Boxer sails for BI

  - 09 June: Coronado pierside in Kona, Boxer offloads K-docks, construction begins

  - 10 June: Refugees begin arriving in late evening, Coronado and Boxer sail to PH

  - 10-15 June: Refugees present, repatriated afternoon of the 15th

  - 15 June: ENDEX, repatriation

  - 15-16 June: Camp breakdown.

  - 17 June: Hotwash on Coronado, in port in Pearl Harbor.

- Physical construction

  - There are two exercise sites, roughly three miles apart, linked by an unpaved road.

### Landmark: Waimea-Kohala Airport

      - Two miles south of the town of Waimea on Hwy 190, the Hawaii Belt Road.

      - Single runway, 5197 feet x 100 feet, paved asphalt. Commercial. Not normally manned.

1. Civil-Military Operations Center site

      - The Waimea-Kohala airport is on the left (east)  side of  Hwy 190, the road coming from Waimea. The CMOC area will be located just off that same Hwy 190. The access gate for the dirt road leading to the CMOC site and the refugee camp is roughly 400 yards south of the airport entrance on the right (west) side of the road when going south. The gate is locked and is controlled by Parker Ranch.

      - The CMOC site is located inside a second access gate, roughly 200 yards from the paved Hwy 190, on the north side of the dirt road, closer to the airport to minimize communication distances. The area is open, so the precise siting of the tents will be at the discretion of the assigned teams.

      - The CMOC site should include tents, with power and light, for:

        - a CMOC

        - for experimentation (TIDES and several others)

        - xxxxxxreg and screen

        - for staff living quarters for 20 outside of the organic CSSG Marine staff

        - for the Coalition Information Bureau (media)

        - for the Coalition Visitors Bureau (DV)

        - a kitchen

        - a dining facility

        - bulk commodities

        - There will be portable latrines on-site

        - There will be a shower unit on-site.

    - Refugee camp site

      - The refugees will be located on the west side of the Puu, 200 yards northwest of a small forest of dead trees and facing the water at the base of the hill. The site is roughly three miles from Hwy 190 on a dirt road curving south around Puu Paa. There is only the single access road from Hwy 190 in past the CMOC site on the right and continuing on to the refugee camp, though there is a tank road running North-South on the west side of the refugee camp area that can provide rough access for a 4WD.

      - Refugee Camp location:

        - 019.59.11  North

        - 155.42.15  West

        - 3400’ altitude

      - Per discussions on the camp site and at the Mid-Planning Conference in San Diego, the refugee camp will be surveyed and constructed by Combat Service Support Group-3 (CSSG-3), Third Marine Regiment, 3rd Marines (Forward), US Marine Corps. The survey and construction will be to standards set by the United Nations and will take place in concert with UN agency staff on site.

      - The refugees will be living in small commercial tents provided on a ratio of roughly one tent per five refugees. The refugees will be responsible for the placement and assembly of the tents within a defined area, coordinated by UN staff.

      - The camp will be open. There will be no enclosing barrier, and there will be no impediment to movement beyond simple safety.

      - CSSG will also manage the camp for sustainment, again in concert with United Nations agencies skilled in the subject areas.

        - WFP for nutrition and bulk commodity management

        - UNICEF for medical support

        - UNHCR for the sustainment of refugee actors to standards set by the UNHCR and the International Committee of the Red Cross (ICRC)

      - The refugee camp site will contain

        - Tents for 125 people using small commercial tents sleeping five refugees per tent, so perhaps 30 tents.

          - no power or light is required for the sleeping tents

        - a shower unit

        - an organic Marine Medical unit

        - portable latrines (contracted)

        - kitchen

        - dining facility

        - recreation

        - administration

        - bulk commodities

        - Marine CSSG staff housing

- Requirements:

  - Road grading x1 on the 4WD access road in late May

  - Water and water storage for 150 non-military people for 6 days, two sites

  - Meals (Tray-pack / MRE / Tray-pack) for 150 non-military people x 6 days, across two sites

  - Portable latrines for 150 non-military for 6 days, two sites

  - Shower services for 150 non-military for 6 days, two sites (Laundry is unlikely)

  - Area Security

  - Media support

  - Experiment support

- Scenario sequence detail

  - Coalition arrival includes a CMOC structure afloat since ethnic persecution is recognized and intervention seems likely.

  - Area of probable refugee migration is inaccessible. Negotiations bring a hesitation to the developing problem.

  - Escalating tensions, refugees recognized in Green, Green asks UN for help.

  - Significant Green infrastructure damage inhibits air transportation to the Green capital at Hilo. Host nation government capital support is untenable.

  - Local US Ambassador discusses it with Green, then the Ambassador requests, through State, Coalition assistance with security, communications, and logistics support to a humanitarian operation. UNSC says Coalition help authorized and appreciated. State notifies SecDef, then CINCPAC, then Coalition JTF Commander (an American)

  - Through concurrent efforts behind the scenes, the CJTF Commander has identified assets to the Theater CINC (ADM Blair).

  - UNSC tasks OCHA to coordinate. OCHA designates UNHCR lead, contacts are made, and civ-mil coordination begins at the Field level. An afloat CMOC desired initially since staff endangerment is likely during the coordination and assessment phase.

  - UN staff brought to Coronado for development of an afloat CMOC.

  - An assessment team is sent ashore by helo. Site selection is done from the air by a Joint Assessment Mission (civ-mil integration) from the Coalition.

  - A list of requirements is generated afloat through a GroupSystems session in the CMOC. Those requirements are passed to military logistics / comms / security.

  - Implementing partners delegated, military fills the gaps:

    - Comms

    - Sustainment

      - Sanitation, food, water, shelter, security

    - Bulk commodity movement

    - Registration and documentation

    - Medical

  - Movement of goods and supplies already underway is refined based on the discussions within the CMOC. Sea-Based logistics through Boxer onload at K-bay, Oahu.

  - Transition CMOC from afloat to ashore once the camp site can sustain adequate civ-mil communications, probably on the 10th of June.

  - Begin receiving refugees once a bare infrastructure is present. Perhaps a bit earlier than preferred.

- Requested from CSSG-3 for CMOC and Refugee Camp (RC) areas (to be amended by CSSG as required)

  - Tents:

    - Eighteen Non-military GP – Medium ( 9 CMOC + 9 RC)

      - RC (9):

        - Medical

        - Recreation (2)

        - Admin

        - Bulk commodity (2)

        - Dining facility (3)

      - CMOC (9)

        - CMOC

        - Non-military staff housing

        - Experimentation

        - Joint Information Center

        - Dining facility

        - Joint Visitors Bureau

        - Press housing

        - Bulk Commodity (2)

  - Latrines, portable:

    - Eighteen  (8 CMOC + 10  RC)

  - Meals:

    - 2700 (150 non-military x 3 meals/day x 6 days)

    - Tray-Pac – MRE - Tray-Pac

  - Water

    - 150 non-military people x 7 days (sustenance + hygiene)

      - drinking

      - cooking

      - shower (CMOC area and Refugee area separated)

      - laundry (optional)

  - Vehicles:

    - Four bulk transport trucks from 09-18 June

    - Three buses on 10 June pm

    - Five buses on 11 June all day

    - 7 buses on 15 June all day

    - Three Ready vehicles (high-occupancy 4WD) for general transport 09-17 June

    - Three Six-Cons for water (CSSG refinement with WFP)

    - Road grader for access road on 05-06 June

  - Cots: 200 non-military

  - Tables, folding: 40

  - Chairs, folding: 100

  - Power/Light modules for tent interior illumination: Eighteen GP-Medium tents (no refugee housing).

  - Area lights:

    - refugee area security

    - CMOC area security

  - Electrical power:

    - Non-lighting power to all non-housing tents.

  - Security detachment:

    - Camp area security

    - CMOC area security

    - VIP/Press escort

      - All areas are unfenced

      - Security is for the protection of the camp, not incarceration. All inhabitants are free to permanently leave at any point and for any reason. We will provide transportation to their embarkation point at their request.

  - Medical

    - Real-world contingency (minor management and major stabilization)

    - Use organic CSSG-3 Medical

      - Competent hospital roughly four miles distant

      - EMS response roughly 15 minutes

      - Air response roughly 4 minutes flight time. Helo locally staged.

      - Radio links to be established early and tested twice daily from RC and CMOC.

  - Manning of CSSG-3 at Third Fleet

    - Provide Senior LNO to Strong Angel beginning at arrival of USS Coronado in Pearl Harbor in late May 2000.

- Health services (screen, baseline, emergency care, routine care, surveillance, vaccinations)

  - Medical support from CSSG-3

  - Link with Fire and Rescue

    - Ensure radio contact

    - Grade road for ambulance access

    - Get precise coordinates for Air-Evac to North Hawaii Community Hospital

  - Get forms for UN landmine injury reporting

  - Get refugee medical reporting forms

  - Get CWAN installed for real-world casualties

- Recreation

  - Red Cross resources

  - Office of Hawaiian Affairs

    - Hawaiian crafts

    - Royal Hawaiian Band

  - Hawaiian Barbeque

  - Refugee presentations (real-world stories)

  - Disaster management presentations (real-world stories)

    - Perhaps LGEN Stackpole from Sea Angel

  - Fitness

  - Games

    - Board

    - Card

    - Sandlot baseball (OTL) and such

  - Ice Cream Social

  - Disney

  - Movies

  - Frisbees

  - Dances

  - Stories

  - Astronomy lectures

  - Geology lectures

  - Nature talks

  - Concerts

- Media collaboration

  - PAO

    - Reuters

    - Discovery Channel

    - UP/AP

    - Navy Times

    - Disney ABC

    - CNN

    - NPR

- Participants

  - US Military

    - Navy (C3F)

    - USMC (CSSG-3)

    - TRANSCOM

    - Air National Guard

    - Army

  - International Organizations

    - IFRC (American Red Cross)

  - UN Agencies

    - OCHA (now in East Timor)

    - UNHCR (currently operating in 40 countries)

    - WFP (currently operating in 80 countries)

    - UNICEF (currently operating in more than 160 countries)

  - Foreign military

    - US

    - Australia

    - Canada

    - Japan probable

  - Civilian refugee actors

    - Age 12 to 70

    - Both sexes

      - Red Cross volunteers (registered, screened, Liability Release signed)

    - Medical screening

    - Liability Release form

    - Liability Release lecture

    - Safety brief

    - Genuine registration to UNHCR-IOM standards

- Communication

  - COMM PLAN frequency allocations (Six total)

  - HF: 3

    - Two HF voice, (MED-1, MED-2) opposite ends of the HF spectrum

      - One HF data (MED-Data)

      - HF voice and data stations with SelCall

      - CODAN 9360 (or NGT)

      - CODAN 9002 modem

        - Both shipboard in JLCC

  - VHF: 5

    - Three VHF voice (Camp1, CMOC Command,  UN-Net)

      - Two VHF data: (CMOC Data-1, CMOC Data-2)

    - VHF personal hand-held (10)

    - VHF repeater

      - On Puu Paa

  - Cellular

    - RIMS email pagers

      - Transceiver on Puu Paa

  - IP addresses

    - In the CMOC spaces

      - just one on the Master Server afloat on Coronado. Use the HF radios

      - Use the JLCC with the Sun Q-70 and the SBBL/J-9 server.

    - On the beach: wireless IP

      - One address

- Shipboard coordination for personnel logistics, berthing, and messing

  - WFP (3 total)

    - 1 (one) O-5 equivalent staff from 04-19 June)

    - 2 Staff passing through to the camp (04-09 June)

  - UNHCR (5 total)

    - 4 passing through to the camp (June 04-09)

    - 1 staying afloat (04-19 June)

  - OCHA

    - 1 afloat from 04-19 June

  - UNICEF

    - 1 afloat from 04-19 June, 2 from 04-09 June

  - COE

    - 2 afloat from 04-19 June

  - CMI

    - 3 afloat from San Diego

  - DARPA-MITRE

    - 1 O-4 equivalent from San Diego

  - Army Civ-Mil

    - 1 O-4 from First Corps from 04-19 June

  - Air Force

    - 1 O-6 from 04-09 June

  - Marines

    - 2 O-4 from 04-19 June

  - Combat Camera

    - Two from 04-19 June

  - Naval Postgraduate School

    - One civilian GS-15 (04-19 June)

- Agency POCs

  - Third Fleet Exercise Coordinator

    - LCDR Eric Rasmussen, MC, USN

      - 619-524-9541 afloat

      - 619-925-7701 cell

      - rasmused@coronado.navy.mil

  - III MEF

    - Third FSSG

      - CSSG-3

        - Major Steve Gabri, G-3

        - (808) 257-1781

        - gabrisj@mcbh.usmc.mil

  - Institute for Interventional Informatics

    - Mark Prutsalis

      - 917-362-4708

      - mprutsalis@hotmail.com

  - Parker Ranch - Pohakaloa Training Area

    - Steve Troute

      - Operations Officer

      - 808-969-2420 office

      - 808-295-0247 cell

  - UN Agencies for participants

    - UNSC

    - OCHA

    - UNHCR

    - WFP

    - UNICEF

  - American Red Cross – Hawaii

    - Glenn Lockwood, State Coordinator

    - Peter Young – Disaster Services Coordinator, West Hawaii

  - RIMPAC Coordinator, Third Fleet

    - LCDR Adam Mroz, RAN

  - K-docks on the Big Island

    - USMC through Steve Troute at PTA

++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++

END